## Sheet1
Project Tasks | Due Date | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July
|  | First-7 | 8-14 | 15-21 | 22-Last | First-7 | 8-14 | 15-21 | 22-Last | First-7 | 8-14 | 15-21 | 22-Last | First-7 | 8-14 | 15-21 | 22-Last | First-7 | 8-14 | 15-21 | 22-Last
Project Set Up | 2020-03-08
Establish communication lines | 2020-03-08
Collaboration spaces(Google docs, Slack, Zoom) | 2020-03-08
Literature Review | 2020-03-15
Problem Definition | 2020-03-25
Establish research question | 2020-03-22
Initial division of research | 2020-03-25
Data Collection/Exploration | 2020-04-15
First Progress Report (Problem Statement/Plan) | 2020-04-01
First Progress Presentation | 2020-04-01
Preliminary Data Analysis | 2020-05-01
Secondary Progress Report (Intro, Lit Review, Data, Methods) | 2020-05-06
Secondary Progress Presentation | 2020-05-06
Final Data Analysis/ML | 2020-06-21
Data Visualizations | 2020-06-21
Website Publishing | 2020-07-19
Set Up Hosting | 2020-06-22
Format/Publish Website | 2020-07-19
Third Progress Report (Pre-final results) | 2020-06-22
Finalize Analytics/Visualisations | 2020-07-15
Final Deliverables (Report, Github, Webpage, Visualization) | 2020-07-20
Final Presentation | 2020-07-23