## Sheet1
Project Tasks | Due Date | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July
|  | First-7 | 8-14 | 15-21 | 22-Last | First-7 | 8-14 | 15-21 | 22-Last | First-7 | 8-14 | 15-21 | 22-Last | First-7 | 8-14 | 15-21 | 22-Last | First-7 | 8-14 | 15-21 | 22-Last
Project Set Up
Establish communication lines
Collaboration spaces(Google docs, Slack, Zoom)
Literature Review
Problem Definition
Establish research question
Initial division of research
Data Collection/Exploration
First Progress Report (Problem Statement/Plan) | 2020-04-01
First Progress Presentation | 2020-04-01
Data Analysis/ML
Secondary Progress Report (Intro, Lit Review, Data, Methods) | 2020-05-06
Secondary Progress Presentation | 2020-05-06
Third Progress Report (Pre-final results) | 2020-06-22
Final Deliverables (Report, Github, Webpage, Visualization) | 2020-07-20
Final Presentation | 2020-07-23